## Summary
Cost Estimate: Stress-Aware Driving App (remaining roadmap, Phases 1 to 3)
Based on the AI PRD roadmap. Phase 0 (prototype) is already built and excluded. US dollars; hours and rates are assumptions you can edit.
Colour legend
Blue text = input
Black text = formula
Green text = pulled from another tab
Yellow fill = key assumption to replace
One-time build cost
Cost item | Lean | Base | Full | Note
Phase 1 Harden | 8531.68 | 13185.96 | 18553.02 | Labor plus non-labor.
Phase 2 Validate | 19159.9 | 32119.85 | 48619.75 | Labor plus non-labor.
Phase 3 Extend | 17290 | 27190 | 38200 | Labor plus non-labor.
One-time subtotal | 44981.58 | 72495.81 | 105372.77
Contingency | 6747.237 | 18123.9525 | 36880.4695 | Subtotal × contingency %.
One-time total | 51728.817 | 90619.7625 | 142253.2395
Running cost and first-year view
Cost item | Lean | Base | Full | Note
Annual run cost | 2893.9992 | 8894.796 | 24258.78 | Steady state after build; see Run Costs tab.
Build plus first year of running | 54622.8162 | 99514.5585 | 166512.0195 | One-time total + one year of run cost.
Labor as share of one-time subtotal | 97.43% | 94.8% | 90.74% | Shows how much of the estimate is people time.
Maintenance as share of annual run cost | 99.52% | 97.14% | 94.98% | Shows what actually drives running cost.
Reading the numbers
Base case: about $90,620 to finish Phases 1 to 3, then about $8,895 a year to run.
People time is 95% of the base build cost, so the rate and hours assumptions matter far more than hardware or SMS fees.
Maintenance is 97% of base annual run cost; SMS costs are negligible at pilot volumes.
Not included in this estimate
1. Real-vehicle use of any kind, ISO 26262 functional-safety validation, and regulatory approval (the PRD rules these out of the roadmap).
2. Medical-device clearance or any diagnostic claim. The product flags distress only.
3. Twilio carrier fees and US A2P registration costs for SMS; verify on Twilio's site.
4. Production cloud deployment, security audits, insurance, legal counsel beyond the allowance, taxes and shipping.
5. Phase 0 (prototype) costs, which are already incurred.
Computer vision options (change in one-time total vs. plan)
Option | Lean | Base | Full | Note
B. Train a custom deep-learning vision model | 13752.85 | 34547.5 | 77538.6 | Added cost; see CV Options tab.
C. Camera only, net of AI-layer rework | -2403.3275 | 3787.75 | 16902.4725 | Negative = saving. Gross saving is larger; see CV Options tab.
Option A (pre-trained face landmarks) is already in the plan and changes nothing.

## Assumptions
Assumptions
Blue = input. Yellow = key assumption to replace with your own numbers. All amounts in US dollars, before tax and shipping.
Scenario drivers
Driver | Lean (solo builder) | Base (small team) | Full (team + external validation) | Basis
Blended engineering rate ($/hour) | 60 | 90 | 120 | ASSUMPTION. Not sourced; replace with your actual rate or contractor quotes.
Overhead on engineering hours (PM, QA, docs) | 10% | 15% | 20% | ASSUMPTION.
Contingency on one-time subtotal | 15% | 25% | 35% | ASSUMPTION. Higher for larger scope and more unknowns.
Validation study participants | 5 | 15 | 30 | ASSUMPTION. Small convenience samples; not a powered clinical study.
Pilot users after build (run phase) | 1 | 5 | 25 | ASSUMPTION.
Alerts per pilot user per month | 1 | 1 | 1 | ASSUMPTION. Escalations should be rare; raise to stress-test.
Cloud hosting ($/month) | 0 | 20 | 100 | ASSUMPTION. The prototype runs locally; cloud is optional.
Maintenance hours per month | 4 | 8 | 16 | ASSUMPTION.
Unit prices
Item | Value | Unit |  | Basis / source
Polar H10 chest sensor | 89.95 | USD each |  | SOURCED (S1): US retailer listing. Other listings seen ranged from about $65 to $130.
Test smartwatch | 250 | USD each |  | ASSUMPTION. Not sourced; depends on the watch model chosen.
Twilio SMS price per segment (US) | 0.0083 | USD per segment |  | SOURCED (S2): 'starts at'. Carrier fees and registration costs are extra and not included.
SMS segments per alert | 2 | segments |  | ASSUMPTION. Alert text is roughly 200 characters.
Cost per alert SMS | 0.0166 | USD per alert |  | Formula.
Twilio local phone number rental | 1.15 | USD per month |  | THIRD-PARTY (S3): summary of Twilio pricing. Verify on Twilio's site.
Participant incentive | 50 | USD per participant |  | ASSUMPTION.
Webcam | 80 | USD each |  | ASSUMPTION.

## Work Breakdown
Work Breakdown (base hours)
Hours are engineering-judgment ASSUMPTIONS mapped to the AI PRD roadmap. Edit the blue cells; everything recalculates.
Phase | Work item | PRD reference | Base hours | Note
Phase 1 Harden | Dead-man's alert for sensor loss | FR-7 | 24 | Highest priority item in the PRD.
Phase 1 Harden | Confidence gate before intervention | FR-8 | 12 | Minimum-readings threshold is still to be set.
Phase 1 Harden | Noise and outlier filter | Roadmap, Phase 1 | 16 | Median or similar filter before scoring.
Phase 1 Harden | Notification retries and acknowledgment | FR-17 | 24
Phase 1 Harden | Emergency contact opt-in flow | Risks table | 16 | Contact must agree before being alerted.
Phase 1 Harden | Log purge and privacy controls | Risks table | 12
Phase 1 Harden | Tests and evals for the above | Evaluation plan | 20
Phase 2 Validate | Replay eval harness | Evaluation plan | 40 | Replays recorded sessions through the pipeline.
Phase 2 Validate | Session recording and labelling tools | Evaluation plan | 40
Phase 2 Validate | Skin tone and motion test protocol | Evaluation plan | 24
Phase 2 Validate | Fairness analysis against chest-strap reference | Evaluation plan | 32
Phase 2 Validate | Watch relay support (phone relay or broadcast) | FR-3 | 80 | Largest single item; depends on the watch chosen.
Phase 2 Validate | Notification flow and sensor dropout evals | Evaluation plan | 24
Phase 2 Validate | Threshold tuning from recorded data | AI requirements | 40
Phase 3 Extend | Camera cross-check (face landmarks) | Roadmap, Phase 3 | 80
Phase 3 Extend | Learned model vs heuristic comparison | AI requirements | 100 | Must beat the heuristic on recorded sessions to replace it.
Phase 3 Extend | Per-driver baseline profiles | Roadmap, Phase 3 | 40
Phase 3 Extend | Integration and evals | Evaluation plan | 40
Phase 0 (Prototype) is already built and is not costed here.

## Labor Costs
Labor Costs by Phase
Base hours × (1 + overhead) × blended rate, per scenario. Phase names must match the Work Breakdown tab.
Phase | Base hours | Hours incl. overhead — Lean | Hours incl. overhead — Base | Hours incl. overhead — Full | Labor cost — Lean | Labor cost — Base | Labor cost — Full
Phase 1 Harden | 124 | 136.4 | 142.6 | 148.8 | 8184 | 12834 | 17856
Phase 2 Validate | 280 | 308 | 322 | 336 | 18480 | 28980 | 40320
Phase 3 Extend | 260 | 286 | 299 | 312 | 17160 | 26910 | 37440
Total | 664 | 730.4 | 763.6 | 796.8 | 43824 | 68724 | 95616

## Non-Labor Costs
Non-Labor Costs
Quantity × unit price per scenario. Allowance rows use a unit price of $1, so the quantity is the dollar amount.
Phase | Item | Unit | Unit price | Qty — Lean | Qty — Base | Qty — Full | Cost — Lean | Cost — Base | Cost — Full | Note
Phase 1 Harden | Polar H10 sensors for development | each | 89.95 | 1 | 1 | 2 | 89.95 | 89.95 | 179.9 | Chest strap used as the BLE reference sensor.
Phase 1 Harden | Test smartwatch for relay and wear checks | each | 250 | 1 | 1 | 2 | 250 | 250 | 500
Phase 1 Harden | Twilio number rental during build | month | 1.15 | 6 | 9 | 12 | 6.9 | 10.35 | 13.8 | Spans all three phases.
Phase 1 Harden | Test alert SMS messages | message | 0.0166 | 50 | 100 | 200 | 0.83 | 1.66 | 3.32 | Carrier fees not included.
Phase 2 Validate | Reference chest-strap sensors for validation study | each | 89.95 | 2 | 3 | 5 | 179.9 | 269.85 | 449.75 | Used as ground truth against wrist data.
Phase 2 Validate | Additional test watch models | each | 250 | 1 | 2 | 3 | 250 | 500 | 750
Phase 2 Validate | Participant incentives | participant | 50 | 5 | 15 | 30 | 250 | 750 | 1500 | Linked to the participants driver.
Phase 2 Validate | Ethics and legal review allowance | USD | 1 | 0 | 1500 | 5000 | 0 | 1500 | 5000 | ASSUMPTION. Human-subject data collection may need formal review; confirm with your institution.
Phase 2 Validate | Data storage and tooling for recorded sessions | USD | 1 | 0 | 120 | 600 | 0 | 120 | 600 | ASSUMPTION.
Phase 3 Extend | Webcam for camera cross-check | each | 80 | 1 | 1 | 2 | 80 | 80 | 160
Phase 3 Extend | Cloud compute for model comparison | USD | 1 | 50 | 200 | 600 | 50 | 200 | 600 | ASSUMPTION. The model is expected to be small.
Totals by phase
Phase 1 Harden | [6 empty] | 347.68 | 351.96 | 697.02
Phase 2 Validate | [6 empty] | 679.9 | 3139.85 | 8299.75
Phase 3 Extend | [6 empty] | 130 | 280 | 760
Total | [6 empty] | 1157.58 | 3771.81 | 9756.77

## Run Costs
Annual Run Costs (steady state after build)
Recurring costs once the product is running with pilot users.
Item | Lean | Base | Full | Note
Pilot users | 1 | 5 | 25 | Linked.
Alerts per user per month | 1 | 1 | 1 | Linked.
Alerts per year | 12 | 60 | 300 | Users × alerts × 12 months.
SMS cost per year | 0.1992 | 0.996 | 4.98 | Alerts × cost per alert SMS. Carrier fees not included.
Twilio number rental per year | 13.8 | 13.8 | 13.8 | Local number, 12 months.
Cloud hosting per year | 0 | 240 | 1200 | Zero if you keep running locally.
Maintenance labor per year | 2880 | 8640 | 23040 | Hours per month × 12 × blended rate.
Annual run cost | 2893.9992 | 8894.796 | 24258.78 | Sum of SMS, number rental, hosting and maintenance.

## CV Options
Computer Vision Options (change vs. the plan)
Illustrative comparison. Option A (pre-trained face landmarks) is already in the plan; B and C show what changes. Blue = input.
Inputs (assumptions)
Input | Lean | Base | Full | Basis
Extra engineering hours for a custom CV model | 160 | 240 | 360 | ASSUMPTION. Data collection and labelling tools, training, evaluation, edge optimisation.
Extra participants for face-video data | 25 | 50 | 100 | ASSUMPTION.
Extra GPU hours for training | 100 | 200 | 400 | ASSUMPTION.
GPU price ($/hour, A100 80GB) | 1.49 | 1.49 | 1.49 | SOURCED (S5): low-cost provider list price. Big cloud providers charge about $3.67 to $5.03 (S6).
Rework hours if the heart signal is dropped (camera only) | 60 | 120 | 180 | ASSUMPTION. The AI layer's scoring is built on BPM and HRV.
Sensor and watch hardware still needed (camera only) | 0% | 0% | 0% | ASSUMPTION. Raise above 0% if you keep a reference sensor.
Baseline pulled from the main model
Item | Lean | Base | Full | Note
Camera cross-check base hours (Phase 3) | 80 | 80 | 80 | Looked up from the Work Breakdown tab.
Camera cross-check labor (incl. overhead) | 5280 | 8280 | 11520 | Hours × (1 + overhead) × blended rate.
Webcam | 80 | 80 | 160 | From the Non-Labor Costs tab.
Camera cross-check cost incl. contingency (already in plan) | 6164 | 10450 | 15768 | Option A. Included in the Summary totals.
Baseline one-time total (main model) | 51728.817 | 90619.7625 | 142253.2395 | Summary tab, one-time total.
Option B: train a custom deep-learning vision model (added cost)
Item | Lean | Base | Full | Note
Extra engineering labor | 10560 | 24840 | 51840 | Extra hours × (1 + overhead) × rate.
Extra participant incentives | 1250 | 2500 | 5000 | Extra participants × incentive per participant.
Extra GPU compute | 149 | 298 | 596 | GPU hours × GPU price. Small next to labor.
Added subtotal | 11959 | 27638 | 57436
Added contingency | 1793.85 | 6909.5 | 20102.6 | Same contingency % as the main model.
Added one-time cost | 13752.85 | 34547.5 | 77538.6
Change vs. plan | 26.59% | 38.12% | 54.51% | Added cost ÷ baseline one-time total.
Option C: camera only (drop the watch and sensor work)
Item | Lean | Base | Full | Note
Watch relay work avoided (FR-3 base hours) | 80 | 80 | 80 | Looked up from the Work Breakdown tab.
Watch relay labor avoided | 5280 | 8280 | 11520 | Hours × (1 + overhead) × rate.
Sensor and watch hardware avoided | 769.85 | 1109.8 | 1879.65 | Phase 1 and 2 sensors and watches, less any hardware still needed.
Subtotal avoided | 6049.85 | 9389.8 | 13399.65
Contingency avoided | 907.4775 | 2347.45 | 4689.8775
Gross saving | 6957.3275 | 11737.25 | 18089.5275 | Before any rework.
Rework of AI layer without the heart signal (incl. contingency) | 4554 | 15525 | 34992 | Rework hours × (1 + overhead) × rate × (1 + contingency).
Net change (negative = saving) | -2403.3275 | 3787.75 | 16902.4725 | Rework minus gross saving.
Net change vs. plan | -4.646% | 4.18% | 11.88% | Net change ÷ baseline one-time total.
Comparison: change in one-time total vs. plan
Option | Lean | Base | Full | Note
B. Custom deep-learning vision model | 13752.85 | 34547.5 | 77538.6 | Added cost.
C. Camera only, gross saving | -6957.3275 | -11737.25 | -18089.5275 | Before rework; negative = saving.
C. Camera only, net of AI-layer rework | -2403.3275 | 3787.75 | 16902.4725 | After the rework allowance; negative = saving.
One-time total with option B | 65481.667 | 125167.2625 | 219791.8395
One-time total with option C (net) | 49325.4895 | 94407.5125 | 159155.712
A. Pre-trained face landmarks is the current plan and changes nothing. Option C also drops the heart signal the PRD relies on, and camera-only accuracy is weaker in poor light or with sunglasses.

## Sources
Sources and Limitations
Prices retrieved October 2026. Everything not listed here is an assumption, marked as such on the Assumptions tab.
ID | Source | Used for | Type | URL | Note
S1 | PlayBetter: Polar H10 Heart Rate Monitor listing | Chest sensor price ($89.95) | US retailer listing | https://www.playbetter.com/collections/polar-heart-rate-monitors | Retail prices vary by seller and sale; listings seen ranged from about $65 to $130.
S2 | Twilio: SMS pricing (United States) | SMS price per segment ($0.0083, 'starts at') | Vendor pricing page | https://www.twilio.com/en-us/sms/pricing | Page states pricing current as of August 2026. Carrier fees are additional.
S3 | Textus: Twilio pricing overview | Local number rental ($1.15/month) | Third-party summary | https://textus.com/blog/twilio-pricing | Not from Twilio directly; verify before committing.
S4 | Stress-Aware Driving App: AI PRD (this conversation) | Roadmap phases, requirement IDs, scope limits | Internal document |  | Defines the work items costed in the Work Breakdown tab.
S5 | Jarvislabs: NVIDIA A100 GPU price in 2026 | GPU price ($1.49/hour, A100 80GB on demand) | Provider blog | https://docs.jarvislabs.ai/blog/a100-price | Snapshot from March 2026; GPU prices change often.
S6 | Hostinger: Cloud GPU pricing compared (2026) | Context: big cloud providers charge about $3.67 to $5.03 per A100 hour | Third-party comparison | https://www.hostinger.com/tutorials/?p=158956 | Prices as of September 2026.
Limitations
1. Engineering hours, rates, allowances and participant counts are assumptions, not quotes. Replace the yellow and blue cells with your own numbers.
2. No salary or contractor-rate source was used; the rate drivers are placeholders for your actual cost.
3. Hardware prices change by retailer and season. The estimate uses one retailer's list price.
4. The computer vision options use illustrative hours, participant counts and GPU hours that are assumptions, not measurements.
5. The estimate covers the PRD's Phases 1 to 3 only, in US dollars, and is an order-of-magnitude planning aid rather than a bid.